## Slide 1
Project Charter
Barrier and Signal Detection · Release 1
Sponsor:
Business owner:
Delivery lead :
Chartered 15 Jun 2026 Release 1 Fri 11 Sep 2026
1 Purpose
Reason over enterprise data to find what stops a therapy reaching patients.
Call notes are the first source; sales, claims and market share from ODP follow.
A common vocabulary: Signal → Barrier → Insight, each traceable to its evidence.
Applies the organization's Knowledge Base and Rulebook exactly. Built on AI Core.
2 Objectives and success
O1 Signals in KB vocabulary, verbatim evidence ·
O2 Barriers at HCP level, rolled up to account ·
O3 Barrier-driven and opportunity insights ·
O4 Released on the production environment ·
Success every write validated · every barrier traceable · re-runs converge · domain sign-off
3 Scope and deliverables
Release 1 signal detection over the first source, call notes · barriers and roll-up · insights · review workbooks and verdicts
Next releases ODP sources: sales, claims, market share · cross-source correlation · further sources as the KB names them
Out recommendations · playbooks and activation
Deliverables solution pack · hub schema · KB-generated taxonomy and rules · workbooks · docs and runbook
4 Requirements (slide 2)
KB and Rulebook applied exactly · evidence enforced · explainable · extensible to further data sources · brand- and therapy-agnostic
5 Milestones
M1 Charter and KB intake · 26 Jun
M2 Hub and taxonomy live · 17 Jul
M3 Signal detection demo · 7 Aug
M4 Domain review · 21 Aug
M5 Code freeze · 4 Sep
M6 Release · 11 Sep
6 Risks, assumptions, constraints
Risk KB revisions mid-build → taxonomy regenerated from the documents
Risk one data source limits correlation → stated; ODP feeds next
Risk model variability → deterministic tiers and gates
Assumes extract in the declared shape · reviewers available · Azure OpenAI and PostgreSQL provisioned
Constraint no platform edits · agents never write the hub directly
7 Stakeholders, governance, approval
Sponsor scope, budget, release
Domain Head Knowledge Base, review sign-off
Delivery lead plan, team
Governance weekly steering · domain review at milestones
Resources delivery lead, platform engineers, domain SMEs, IT · budget per SOW [confirm]
Exit smoke test on the production environment · domain sign-off · runbook handed over

## Slide 2
Project Requirements
From the Knowledge Base and the Rulebook
Business requirements
Enterprise data first; any dataset the KB names SIG-1, 3
Every applicable signal, KB vocabulary only SIG-2, 6
Evidence traceable to the source record SIG-5, BAR-8, INS-4
Directional signals need comparable periods SIG-7
Correlate first; keep contradictions COR-1, 3
Barriers only from KB-mapped signals, never forced BAR-6, 13
Three insight paths, no recommendations INS-2, 6
Inactive signals and barriers excluded USE-CASE-1
Human review; verdicts survive re-runs
Brand-, therapy- and vendor-agnostic
Functional
Sources Release 1: call notes · Release 2: ODP: sales, claims, market share
Detection rules as the floor, agent adjudication on top
Grain HCP, rolled up to account
Scores confidence, severity, priority: computed, never written
Re-runs idempotent; remediate step
Review workbooks, evidence walk, traceability graph
Ask the analyst agent; the answer carries its SQL
Non-functional
Extensible: a new dataset is a declared source with its own rulebook; the taxonomy is constant
Installable pack on AI Core; no platform edits
PostgreSQL in production; SQLite for developers
Azure OpenAI through the enterprise tenant
Resilient: retries, attempt caps, self-healing runs
Forensics per run; auditable rule enforcement
The KB's reasoning hierarchy
Enterprise data
Signal
Correlation
Barrier / Opportunity
Insight
Review

## Slide 3
Solution on the AI Core
One solution, four layers
Users
Brand and domain teams
Studio · review workbooks
Field and functional teams
barrier register by account and HCP
Operations
one command per data drop
Barrier and Signal Detection
Signal detection
Barrier detection
Insights and brief
Review and verdicts
Three agents
Ava prepares · Maya detects · Vera verifies
Knowledge Base and Rulebook
192 signal types · 20 barrier types · 34 rules, as data
Validating tools
every write is checked against the KB
AI Core Platform
Data sources and stores
Release 1 · Call notes
the first source
Release 2 · ODP
One Data Platform: sales · claims · market share
Hub
signals · barriers · insights · verdicts
The solution supplies the judgement. The platform supplies scheduling, recovery, evidence gates, forensics and security. A new data source is a declared source with its rulebook; the taxonomy and the base do not change.

## Slide 4
Project Achievements
What the business gains, and who acts on it
Every record is read
call notes first; more sources next
20 obstacle types
across 6 business areas
Evidence behind every barrier
the source record, verbatim
HCP, then account
the level a response is planned at
Any brand
a new brand is configured, not rebuilt
What the business can now answer
Where is the therapy blocked, and by what? a ranked register by account and HCP
Is it real? every barrier walks back to a sentence; a person records the verdict
What do we do on Monday? priority, severity, and the function that owns each obstacle
What is going right? opportunity insights, reported separately from barriers (INS-3)
Can we do this for other brands? yes: a taxonomy configuration, not a rebuild
Who acts on it
Brand leadership one evidence-backed view; a signal brief for the leadership meeting
Market access formulary, step therapy and coverage obstacles, by account
Patient services prior-auth and enrolment delays, where support is needed
Medical affairs evidence requests and efficacy concerns, as HCPs raised them
Field operations engagement and coverage gaps; every note is read
Compliance safety signals excluded as configured; an audit trail to the sentence
Built and verified in code
192 signal types · 20 barrier types · 256 admitted mappings, enforced at write time · 32 of 34 Rulebook rules enforced in code or schema · re-runs converge · deployable on the organization's infrastructure

## Slide 5
Project Plan
Release 1 · Friday 11 Sep 2026 · 13 weeks from 15 Jun
Jun
Jul
Aug
Sep
W1 · 15
W2 · 22
W3 · 29
W4 · 6
W5 · 13
W6 · 20
W7 · 27
W8 · 3
W9 · 10
W10 · 17
W11 · 24
W12 · 31
W13 · 7
Phase
Mobilise and discovery
charter · KB and Rulebook intake · environments
Data foundation
hub · taxonomy and rules from the KB
Signal detection
two tiers · correlation · coverage
Barrier detection and insights
KB-gated · scoring · integrity gate · workbooks
Hardening
HCP level · idempotent re-runs · deployment
Release
UAT · smoke test · go / no-go · handover
Testing and forensics
continuous
Documentation and enablement
docs · runbook · developer walk
Weekly steering
Milestones
M1 Charter · 26 Jun
M2 Hub live · 17 Jul
M3 Signals demo · 7 Aug
M4 Domain review · 21 Aug
M5 Code freeze · 4 Sep
M6 Release · 11 Sep